## Dashboard
Operational Efficiency Dashboard
Metric | Result |  | Metric | Current | Target | Bottleneck | Delay
Registration time saved | 8 |  | Registration | 18 | 10 | Check-in | 8
Patient waiting time reduced | 15 |  | Waiting | 35 | 20 | Insurance | 7
Daily registration minutes saved | 480 |  | Confirmation | 25 | 12 | Records | 4
Monthly admin hours saved | 176 |  | Records | 9 | 5 | Department | 6
Estimated monthly cost saving | 7920 |  | Insurance | 14 | 7 | Status update | 5
Same-day resolution target | 90 |  |  |  |  | Escalation | 5
Improvement Status | Count | Share
Not Started | 2 | 33.33%
In Progress | 3 | 50%
Completed | 1 | 16.67%
Total | 6

## Efficiency Data
Process Area | Metric | Current Performance | Improved Target | Unit | Gap | Improvement % | Daily Volume | Daily Minutes Saved
Patient Registration | Average registration time | 18 | 10 | minutes | 8 | 44.44% | 60 | 480
Patient Waiting | Average waiting time | 35 | 20 | minutes | 15 | 42.86% | 60 | 900
Appointment Coordination | Appointment confirmation delay | 25 | 12 | minutes | 13 | 52% | 40 | 520
Medical Records | Record retrieval time | 9 | 5 | minutes | 4 | 44.44% | 35 | 140
Insurance Review | Insurance approval delay | 14 | 7 | minutes | 7 | 50% | 45 | 315
Record Accuracy | Duplicate record rate | 8 | 3 | % | 5 | 62.5% | 60
Issue Resolution | Same-day issue resolution | 70 | 90 | % | -20 | -28.57% | 25

## Bottleneck Analysis
Bottleneck ID | Process Step | Issue | Root Cause | Current Delay (min) | Impact | Recommended Action | Owner | Priority | Status
BN-001 | Patient check-in | Details verified after arrival | No pre-visit checklist | 8 | Longer registration queue | Create daily pre-visit verification checklist | Front Desk Lead | High | In Progress
BN-002 | Insurance review | Approval checked at the counter | Insurance status not reviewed before visit | 7 | Patient wait time increases | Review insurance status one day before appointment | Billing Officer | High | In Progress
BN-003 | Records search | Duplicate patient records found | No duplicate check field | 4 | Incorrect record selection risk | Use patient ID and mobile number duplicate check | Records Officer | Medium | Not Started
BN-004 | Department confirmation | Availability confirmed late | No shared capacity view | 6 | Department handoff delay | Use shared capacity board and morning huddle | Outpatient Coordinator | High | In Progress
BN-005 | Status update | Appointment status updated twice | Separate department trackers | 5 | Repeated data entry | Create one shared appointment status tracker | Operations Supervisor | Critical | Not Started
BN-006 | Issue escalation | Unclear owner for delays | No time-based escalation rule | 5 | Delayed case resolution | Assign escalation rules by issue type | Quality Coordinator | Medium | Completed

## Improvement Tracker
Action ID | Improvement Action | Process Area | Owner | Start Date | Due Date | Priority | Status | Progress % | Expected Benefit | Notes
IMP-001 | Introduce pre-visit verification checklist | Patient Registration | Front Desk Lead | 2026-06-15 | 2026-06-30 | High | In Progress | 5500% | Reduce registration time by 4 minutes | Checklist includes ID, contact details, appointment status, and required documents
IMP-002 | Build shared appointment and insurance tracker | Appointment Coordination | Operations Supervisor | 2026-06-15 | 2026-07-15 | Critical | Not Started | 1500% | Reduce repeated updates and improve visibility | Tracker includes patient ID, department, insurance, status, and owner
IMP-003 | Review insurance status one day before appointments | Insurance Review | Billing Officer | 2026-06-20 | 2026-07-05 | High | In Progress | 4500% | Reduce approval delays by 50% | Use next-day appointment list for pre-checks
IMP-004 | Create duplicate record prevention rules | Medical Records | Records Officer | 2026-06-20 | 2026-07-10 | Medium | Not Started | 2000% | Lower duplicate record rate to 3% | Validation rule uses patient ID and mobile number
IMP-005 | Start 10-minute daily department huddle | Interdepartmental Coordination | Outpatient Coordinator | 2026-06-17 | 2026-06-24 | Medium | Completed | 10000% | Reduce department confirmation delays | Review capacity, urgent cases, and unresolved issues
IMP-006 | Implement escalation rules for unresolved cases | Interdepartmental Coordination | Quality Coordinator | 2026-06-25 | 2026-07-20 | High | In Progress | 3500% | Improve same-day resolution to 90% | Escalate based on issue type and time limit

## Time Savings Calculator
Input / Output | Value | Unit | Formula / Notes
Average patients per day | 60 | patients | Editable input
Working days per month | 22 | days | Editable input
Registration time saved per patient | 8 | minutes | Current registration time minus improved target
Daily registration minutes saved | 480 | minutes | Patients per day multiplied by time saved
Monthly registration hours saved | 176 | hours | Daily minutes saved multiplied by working days / 60
Estimated admin cost per hour | 45 | AED | Editable input
Estimated monthly admin cost saving | 7920 | AED | Monthly hours saved multiplied by cost per hour
Patient waiting time reduction per patient | 15 | minutes | Current waiting time minus improved target
Daily patient waiting minutes reduced | 900 | minutes | Patients per day multiplied by waiting time reduction

## KPI Tracker
KPI | Baseline | Target | Current Month | Status | Owner | Review Frequency | Formula / Rule
Average registration time | 18 | 10 | 14 | Needs Action | Front Desk Lead | Weekly | On Track if current month is less than or equal to target
Average patient waiting time | 35 | 20 | 27 | Needs Action | Operations Supervisor | Weekly | On Track if current month is less than or equal to target
Appointment confirmation delay | 25 | 12 | 18 | Needs Action | Outpatient Coordinator | Weekly | On Track if current month is less than or equal to target
Duplicate record rate | 8 | 3 | 5 | Needs Action | Records Officer | Monthly | On Track if current month is less than or equal to target
Same-day issue resolution | 70 | 90 | 82 | Needs Action | Quality Coordinator | Weekly | On Track if current month is greater than or equal to target
Corrective action closure | 75 | 90 | 84 | Needs Action | Quality Coordinator | Monthly | On Track if current month is greater than or equal to target

## Workflow Map
Current Workflow Step | Description | Pain Point | Improved Workflow Step | Description | Expected Result
1 | Patient arrives at reception | Queue builds during peak hours | 1 | Next-day appointment list is prepared | Exceptions identified before patient arrival
2 | Appointment is searched | Search may use name instead of unique patient ID | 2 | Patient record and insurance status are reviewed | Registration starts with clear status
3 | Patient details are verified | Repeated entry when details already exist | 3 | Department capacity is checked during morning huddle | Availability is visible to front desk
4 | Insurance status is checked | Approval issue identified late | 4 | Patient arrives and details are confirmed | Only required changes are updated
5 | Department availability is confirmed | Staff must call or message department | 5 | Appointment status is updated in one shared tracker | Departments see the same information
6 | Record is retrieved or corrected | Duplicate records slow down selection | 6 | Patient is directed to service area | Waiting time is reduced
7 | Patient waits for final confirmation | Waiting time increases | 7 | Unresolved cases follow escalation rules | Ownership and time limits are clear
8 | Status is updated after service | Updates may be duplicated across trackers | 8 | Daily KPI dashboard is reviewed | Continuous improvement is supported

## Validation Lists
Status | Priority | Owner | Process Area | Risk Level
Not Started | Low | Front Desk Lead | Patient Registration | Low
In Progress | Medium | Records Officer | Appointment Coordination | Medium
Completed | High | Billing Officer | Insurance Review | High
On Hold | Critical | Outpatient Coordinator | Medical Records | Critical
Pending Review |  | Operations Supervisor | Interdepartmental Coordination
Closed |  | Quality Coordinator | Billing Coordination