## Dashboard
Patient Experience Strategy Dashboard
Outpatient Clinic Administration ¦ Patient Service, Wait Time, Feedback, Training, and Quality Monitoring
Metric | Current | Target | Gap | Budget Summary | Amount | Notes
Average Front Desk Wait Time | 18 | 10 | 8 | Planned Budget | 6500 | Initial 3-month plan
Patient Satisfaction Score | 78% | 90% | 12% | Actual Spend | 6000 | Based on budget tracker
Appointment Confirmation Accuracy | 85% | 97% | 12% | Variance | 500 | Positive means under plan
Complaint Closure Within 48 Hours | 70% | 95% | 25% | Main Cost Area | Staff Training | Largest planned item
Record Readiness Before Visit | 80% | 95% | 15%
Missed Appointment Rate | 12% | 7% | 5%
Service Area | Baseline Score | Target Score | Status | Improvement Focus | Owner | Due
Front Desk Communication | 3.7 | 4.5 | Action Needed | Introduce patient check-in checklist | Front Desk Lead | 2026-07-10
Appointment Updates | 3.6 | 4.6 | Action Needed | Launch appointment reminder process | Clinic Coordinator | 2026-07-17
Record Preparedness | 3.8 | 4.5 | Action Needed | Start weekly feedback review | Patient Relations Officer | 2026-07-24
Billing Clarity | 3.5 | 4.4 | Action Needed | Complete staff service training | Training Lead | 2026-08-07
Overall Experience | 3.9 | 4.6 | Action Needed | Publish monthly KPI report | Quality Coordinator | 2026-08-31

## Feedback Tracker
Patient Feedback Tracker
Feedback ID | Date | Patient Type | Touchpoint | Front Desk Score | Wait Time Score | Communication Score | Records Handling Score | Overall Score | Comment Theme | Action Required | Owner | Status | Closure Date
FB-001 | 2026-07-01 | Returning Patient | Front Desk | 4 | 3 | 4 | 4 | 3.75 | Queue delay | Review peak-hour coverage | Front Desk Lead | In Progress
FB-002 | 2026-07-01 | New Patient | Appointment Scheduling | 3 | 3 | 3 | 4 | 3.25 | Appointment update | Confirm reminder timing | Clinic Coordinator | In Progress
FB-003 | 2026-07-02 | Follow-up Patient | Medical Records | 4 | 4 | 4 | 3 | 3.75 | Document request | Update document checklist | Records Officer | Completed | 2026-07-04
FB-004 | 2026-07-03 | Returning Patient | Billing | 3 | 4 | 3 | 4 | 3.5 | Billing clarity | Improve fee explanation script | Patient Relations Officer | Not Started
FB-005 | 2026-07-03 | Family Member | Nursing Handover | 4 | 4 | 4 | 4 | 4 | Clear directions | Maintain standard process | Quality Coordinator | Completed | 2026-07-05
FB-006 | 2026-07-04 | New Patient | Front Desk | 3 | 2 | 3 | 3 | 2.75 | Long wait | Open second desk during peak hour | Administration Supervisor | At Risk
FB-007 | 2026-07-05 | Returning Patient | Follow-up | 4 | 3 | 4 | 4 | 3.75 | Follow-up details | Send written follow-up summary | Clinic Coordinator | In Progress
FB-008 | 2026-07-05 | New Patient | Pharmacy | 4 | 4 | 4 | 4 | 4 | Clear guidance | Share best practice with team | Quality Coordinator | Completed | 2026-07-06
FB-009 | 2026-07-06 | Follow-up Patient | Appointment Scheduling | 3 | 3 | 3 | 3 | 3 | Reschedule update | Improve change notification script | Clinic Coordinator | Not Started
FB-010 | 2026-07-06 | Returning Patient | Medical Records | 4 | 4 | 4 | 4 | 4 | Prepared file | Continue pre-check routine | Records Officer | Completed | 2026-07-07

## KPI Monitoring
Patient Experience KPI Monitoring
Metric | Baseline | Month 1 | Month 2 | Month 3 | Target | Direction | Status | Owner
Average Front Desk Wait Time | 18 | 16 | 13 | 10 | 10 | Lower is Better | On Track | Front Desk Lead
Patient Satisfaction Score | 78% | 82% | 86% | 90% | 90% | Higher is Better | On Track | Patient Relations Officer
Appointment Confirmation Accuracy | 85% | 90% | 94% | 97% | 97% | Higher is Better | On Track | Clinic Coordinator
Complaint Closure Within 48 Hours | 70% | 78% | 88% | 95% | 95% | Higher is Better | On Track | Administration Supervisor
Record Readiness Before Visit | 80% | 86% | 91% | 95% | 95% | Higher is Better | On Track | Records Officer
Missed Appointment Rate | 12% | 10% | 8% | 7% | 7% | Lower is Better | On Track | Clinic Coordinator

## Implementation Timeline
Patient Experience Implementation Timeline
Phase | Month | Initiative | Start Date | End Date | Owner | Deliverable | Status | Progress
Phase 1: Assessment | Month 1 | Review patient complaints and feedback themes | 2026-07-01 | 2026-07-07 | Patient Relations Officer | Feedback summary | Completed | 100%
Phase 1: Assessment | Month 1 | Measure wait time at front desk and key service points | 2026-07-01 | 2026-07-10 | Front Desk Lead | Wait time baseline | Completed | 100%
Phase 2: Process Update | Month 2 | Launch check-in checklist and document readiness review | 2026-07-15 | 2026-08-05 | Records Officer | Updated checklist | In Progress | 65%
Phase 2: Process Update | Month 2 | Introduce appointment reminder and change update process | 2026-07-20 | 2026-08-10 | Clinic Coordinator | Reminder tracker | In Progress | 55%
Phase 3: Training | Month 3 | Complete service quality and complaint handling training | 2026-08-01 | 2026-08-20 | Training Lead | Training attendance log | Not Started | 20%
Phase 3: Monitoring | Month 3 | Publish monthly dashboard and improvement review | 2026-08-15 | 2026-08-31 | Quality Coordinator | KPI report | Not Started | 10%

## Budget Tracker
Patient Experience Budget Tracker
Item | Category | Planned Cost | Actual Cost | Variance | Owner | Status | Notes
Staff service training | Training | 3000 | 2800 | 200 | Training Lead | In Progress | Communication and complaint handling
Digital feedback form setup | Technology | 500 | 450 | 50 | Patient Relations Officer | Completed | QR form and monthly feedback export
Queue tracking sheet and dashboard | Technology | 1000 | 950 | 50 | Front Desk Lead | In Progress | Daily wait-time monitoring
Reminder message process | Communication | 1200 | 1100 | 100 | Clinic Coordinator | In Progress | Confirmation and reminder tracker
Printed patient information materials | Communication | 800 | 700 | 100 | Administration Supervisor | Not Started | Clear visit steps and required documents
Total |  | 6500 | 6000 | 500

## Staff Training
Staff Training Plan
Training Topic | Audience | Delivery Date | Trainer | Completion Target | Completion Actual | Status | Evidence
Patient communication etiquette | Front desk and administration staff | 2026-08-03 | Training Lead | 100% | 80% | Scheduled | Attendance sheet
Complaint handling and service recovery | Patient-facing staff | 2026-08-05 | Patient Relations Officer | 100% | 70% | Scheduled | Scenario practice checklist
Appointment coordination standards | Front desk and clinic coordinators | 2026-08-07 | Clinic Coordinator | 100% | 75% | Scheduled | Scheduler quality review
Confidentiality and data protection | All administration staff | 2026-08-10 | Quality Coordinator | 100% | 85% | Scheduled | Acknowledgment form
Feedback review and improvement actions | Leads and supervisors | 2026-08-12 | Administration Supervisor | 100% | 60% | Planned | Monthly review template

## Complaint Resolution
Complaint Resolution Tracker
Case ID | Date Received | Category | Issue Summary | Priority | Assigned To | Target Closure Date | Closure Date | Days to Close | Status | Root Cause | Corrective Action
CR-001 | 2026-07-01 | Waiting Time | Patient waited over expected front desk time | High | Front Desk Lead | 2026-07-03 | 2026-07-02 | 1 | Closed on Time | Peak-hour staffing gap | Add second front desk coverage at busy periods
CR-002 | 2026-07-02 | Communication | Appointment change was not explained clearly | Medium | Clinic Coordinator | 2026-07-04 |  | -20 | Open | No standard update script | Use patient update script for schedule changes
CR-003 | 2026-07-04 | Records | Patient was asked for the same document twice | Medium | Records Officer | 2026-07-06 | 2026-07-06 | 2 | Closed on Time | Document status not visible | Add document-ready field in tracker
CR-004 | 2026-07-05 | Billing | Patient needed clearer information about payment step | Low | Patient Relations Officer | 2026-07-08 |  | -23 | Open | Unclear handover | Provide short billing guidance note
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
[8 empty] | 46185 | Open
Formulas:
Days to Close = IF([Closure Date]="",TODAY()-[Date Received],[Closure Date]-[Date Received])

## Patient Journey
Patient Journey Improvement Map
Journey Step | Current Pain Point | Improvement Action | Tool / Template | Responsible Team | KPI | Expected Benefit | Status
Appointment booked | Patient may not receive clear confirmation | Send confirmation with date, time, location, and required documents | Appointment confirmation tracker | Clinic Coordinator | Confirmation accuracy | Fewer missed visits | In Progress
Pre-visit preparation | Records may not be ready before arrival | Complete document check one day before appointment | Document readiness checklist | Records Officer | Record readiness | Shorter registration time | In Progress
Arrival and check-in | Queue may build during peak hours | Track arrival time and assign second counter when needed | Queue monitoring dashboard | Front Desk Lead | Wait time | Lower patient frustration | Not Started
Department handover | Patient may not know next step | Use clear handover note and direction script | Patient direction script | Nursing Handover | Service clarity score | Better patient confidence | Not Started
Billing or pharmacy step | Payment or collection steps may be unclear | Provide brief written guidance and staff explanation | Patient information note | Billing | Billing clarity score | Reduced confusion | Not Started
Feedback and follow-up | Feedback may not be reviewed regularly | Collect and review feedback every month | Feedback tracker | Patient Relations Officer | Satisfaction score | Continuous improvement | In Progress

## Action Plan
Patient Experience Action Plan
Action ID | Initiative | Priority | Owner | Start Date | Due Date | Status | Progress | Dependency | Notes
A-001 | Introduce front desk check-in checklist | High | Front Desk Lead | 2026-07-01 | 2026-07-15 | In Progress | 70% | Approved checklist | Pilot during morning peak
A-002 | Start pre-visit record readiness review | High | Records Officer | 2026-07-05 | 2026-07-20 | In Progress | 60% | Patient list from scheduler | Review one day before visit
A-003 | Launch reminder and change update process | High | Clinic Coordinator | 2026-07-10 | 2026-07-30 | Not Started | 25% | Updated contact fields | Use consistent wording
A-004 | Create patient feedback QR form | Medium | Patient Relations Officer | 2026-07-12 | 2026-07-25 | Completed | 100% | Approved questions | Include rating and open comment
A-005 | Deliver service quality training | Medium | Training Lead | 2026-08-01 | 2026-08-15 | Not Started | 10% | Training material ready | Include confidentiality reminder
A-006 | Review KPI dashboard every month | Medium | Quality Coordinator | 2026-08-01 | 2026-08-31 | Not Started | 10% | Dashboard updated | Share with department leads

## Validation Lists
Status | Priority | Touchpoint | Category | Owner | Training Status | Direction | Patient Type
Not Started | Low | Front Desk | Waiting Time | Front Desk Lead | Planned | Higher is Better | New Patient
In Progress | Medium | Appointment Scheduling | Communication | Administration Supervisor | Scheduled | Lower is Better | Returning Patient
Completed | High | Medical Records | Records | Patient Relations Officer | Completed |  | Follow-up Patient
At Risk | Urgent | Billing | Billing | Records Officer | Follow-up Required |  | Family Member
On Hold |  | Nursing Handover | Appointment | Clinic Coordinator
|  | Pharmacy | Staff Courtesy | Quality Coordinator
|  | Follow-up | Service Clarity | Training Lead